## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Tech Elite (Group L) | Completed | 11
Project title | Commercial livestock marketplace and record-keeping application | In Progress | 0
Stakeholder or organisation | Kgomotso Ranchu | Not Started | 0
Group mentor |  | Delayed | 0
Reporting phase | Unit 1 / Phase 1 | Blocked | 0
Reporting period |  | Overdue | 0
Overall status | Completed
Overall % complete | 83.33% | Contribution Summary | Count
Main achievement | 1.Identify stakeholder and understand his main problem. 2.Develop all documentation to define requirements, scope,risks, problems and solutions. 3.Develop Microsoft project for tracking progress. 4.Establish GitHub repository for project collaboration. 5.Complete the progress tracker on the excel sheet and prepare for presentation of the project | Contribution entries | 8
Main challenge | 1.Ensuring that every member's part is consistent and has the same format. 2.Microsoft plan cannot be completed without members submitting all relevant information | Verified entries | 8
Next planned activity | 1. Review all documentation to check, consistency, grammar and mistakes. 2. Update progress tracker and Microsoft plan. 3. Prepare for the presentation and submit before the 04th of September 2026. | Unverified entries | 0
|  | Stakeholder engagements | 0

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Kali L | 20/08/26 | 31/08/26 | Completed | 100 | Stated in the Stakeholder Engagement and Evidence document | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Koloi L | 20/08/26 | 31/08/26 | Completed | 100 | Stakeholder and Problem Analysis document | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | Mthembu BKD | 20/08/26 | 31/08/26 | Completed | 100 | Project Scope and Integrated Solution document | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Koloi L | 20/08/26 | 31/08/26 | Completed | 100 | Stakeholder and Problem Analysis document | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | Kali L | 20/08/26 | 31/08/26 | Completed | 100 | Stakeholder Engagement and Evidence document | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | Mangoejane O | 20/08/26 | 31/08/26 | Completed | 100 | Requirements Analysis and SRS document | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Taeli MW | 20/08/26 | 31/08/26 | Completed | 100 | Microsoft Project plan | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | Masimong B | 27/08/26 | 31/08/26 | Completed | 100 | GitHub | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | Kali L | 27/08/26 | 31/08/26 | Completed |  |  | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Masimong B | 28/08/26 | 31/08/26 | Completed | 100 | Progress report Excel sheet | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | All members | 28/08/26 | 31/08/26 | Completed | 100 | Documents in the zip folder | Yes |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Boitumelo Masimong | 224091294 | Unit 1 / Phase 1 | Project management:Github and Progress Tracker | Create a GitHub repository for the project , ensure all members accept the invitation and become collaborators of the project.Allocate tasks to every member and monitor the progress. Ensure that the work of the team is recorded throughout the phase. | Completed Project Progress tracker and created a GitHub repository. | 28/08/26 | 56h | Progress tracker document | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Mampuku Taeli | 222082043 | Unit 1 / Phase 1 | Microsoft Project Plan | Create a project schedule in Microsoft Project to track activity progress, start time, end time, deadlines, milestones and get the overall project timeline. | Completed the plan on Microsoft Project and provided a timeline. | 28/08/26 | 56h | Microsoft Project Plan | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Lebohang Koloi | 224132354 | Unit 1 / Phase 1 | Stakeholder and Problem Analysis | Create a document that outlines all the problems of our Stakeholder (Kgomotso Rachu). Needs , problems and expectations are clearly defined. | Completed Stakeholder and Problem Analysis document by providing the main problems that must be solved by the team. | 28/08/26 | 48h | Stakeholder and Problem Analysis document | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Lucky Kali | 221045002 | Unit 1 / Phase 1 | Stakeholder Engagement and Evidence | Communicates directly with stakeholder,schedule a meeting and document the team's engagement with the stakeholder. Screenshot calls, texts and meeting minutes with the stakeholder. | Completed Stakeholder Engagement and Evidence document by giving meetings and communication evidence. | 28/08/26 | 48h | Stakeholder Engagement and Evidence document | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Omolemo Mangoejane | 224036084 | Unit 1 / Phase 1 | Requirements Analysis and SRS | Gather all requirements that the stakeholder expects on the app/system. Document functional, non-functional requirements and provide a requirement analysis. | Completed Requirements Analysis and SRS by providing a document that lists all requirements. | 28/08/26 | 48h | Requirements Analysis and SRS document | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Talente Mokgwati | 223022927 | Unit 1 / Phase 1 | Project Risk Analysis | Identifies risks, the impact that each risk will have and mitigation plans. A risk register must be developed to assist with the risk evaluation. | Completed Project Risk Analysis document by providing a document that lists all risks and strategies to reduce the risks. | 28/08/26 | 48h | Project Risk Analysis document | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Bokang Mthembu | 224063836 | Unit 1 / Phase 1 | Project Scope and Integrated Solution | Defines the objectives, deliverables and elaborate on how the solution integrates with the project requirement | Completed Project Scope and Integrated Solution document by defining scope, deliverables and the project's integration solution. | 28/08/26 | 48h | Project Scope and Integrated Solution document | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Rethabile Mosia | 223013027 | Unit 1 / Phase 1 | Feasibility Analysis | Provide an analysis on technical, economic/financial, operational,schedule and organisational feasibility. This analysis will state whether the project should continue or not | Completed Feasibility Analysis document by providing technical,economic,operational and schedule and organisational feasibility of the project. | 28/08/26 | 48h | Feasibility Analysis document | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
20/08/26 | Unit 1 / Phase 1 | Telephone Call | The meeting was held to get approval from the stakeholder. | Lucky Kali | Mr Kgomotso Rachu(Business Representative) | Lucky spoke about the stakeholder letter to get permission from the stakeholder. The stakeholder confirmed his availability. | Tech Elite requested a meeting with the stakeholder and Lucky assisted with making meeting arrangements | Stakeholder Engagement and evidence
20/08/26 | Unit 1 / Phase 1 | Meeting | The meeting was held to introduce Tech Elite (Group members) to Kgomotso Ranchu (Stakeholder). | All members(Omolemo Mangoejane, Mampuku Taeli, Lebohang Koloi,Bokang Mthembu,Rethabile Mosia, Lucky Kali,Talente Mokgwati, Boitumelo Masimong) | Mr Kgomotso Rachu(Business Representative) | The team got to understand the problem of the stakeholder, his requirements and everything was based on the needs of the business rather than our own assumptions. | The team took note of all points discussed and used them to do the documentation. The problem and requirements were analysed.The information gathered will be used to address business needs. | Stakeholder Engagement and evidence

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
21/08/2026 | Unit 1 / Phase 1 | Challenge faced was that the initial scope conducted by the team member was too short and not well detailed that they had to refer back to the minutes we took during our meeting with the stakeholder in order to fulfill all requirements |  | Referred to Unit 1 and Unit 2 and followed the format required. | Bokang Mthembu | 31/08/2026 | Resolved
27/08/2026 | Unit 1 / Phase 1 | Challenge faced was that the feasibility analysis provided by the member was missing the most important tasks of the project required by the stakeholder. |  | Guidance from the assesment requirements and ensure all areas were covered properly. | Rethabile Mosia | 31/08/2026 | Resolved
27/08/2026 | Unit 1 / Phase 1 | Challenges faced was not understanding how to translate information obtained from the stakeholder into a clear and well defined problem statement. |  | Addressed this by focusing on the main issue identified during the engagement and ensuring that problem analysis reflected the stakeholder's needs rather than assumptions. | Lebohang Koloi | 31/08/2026 | Resolved
27/08/2026 | Unit 1 / Phase 1 | Challenges faced by the Microsoft Project Planner was developing a realistic and well structured project schedule. |  | Reviewed the project requirements and regularly communicated with the group members to confirm task responsibilities, progress and expected completion dates. | Mampuku Taeli | 31/08/2026 | Resolved
20/08/2026 | Unit 1 / Phase 1 | Challenge faced was that the team member struggled to assign members to do specific tasks according to their strengths. |  | Communicated with the group members to understand their areas of interest and capabilities. | Boitumelo Masimong | 31/08/2026 | Resolved
27/08/2026 | Unit 1 / Phase 1 | Difficulty identifying all possible project risks at the beginning. |  | Consulted with group members to identify potential risks based on their tasks and responsibilities. | Talent Mokgwati | 31/08/2026 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | No
Reporting period |  | Progress report updated | No
Overall phase status | Not Started | Individual contributions recorded | No
What was completed during this phase? |  | Stakeholder engagement recorded | No
What remains incomplete? |  | Challenges and actions updated | No
Why is it incomplete? |  | Group reflection completed | No
Which contributions were particularly important? |  | Microsoft Project updated | No
Were there participation concerns? |  | GitHub evidence available | No
What will the group improve in the next phase? |  | Confidential peer check completed | No
Main priority for the next phase

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300–400 words in total.
Project title |  | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase |  | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? |  | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? |  | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members?
Did all members contribute fairly? Explain.
How did the group handle disagreements or delays?
What did the group learn from the stakeholder?
Improvement action 1 for the next phase
Improvement action 2 for the next phase
Priority for the next phase