## Instructions
ITC327W Phase 2 Project Progress Tracker
Use this workbook during Phase 2: System Architecture and Design. Update it throughout the phase and submit the same workbook with Assessment 2.
Sheet | Purpose | What must be kept current
Project Overview | Group details and automatic progress summary | Group information, GitHub link and current Phase 2 progress
Design Progress | Track each design artefact and supporting work | Architecture, UML, ERD, mobile/web interfaces, SRS and project-management tasks
Individual Contributions | Record work personally completed by each student | Activity, responsibility, work completed and evidence
Design Source Links | Record editable source links/files for submitted designs | Architecture, UML, ERD, mobile and web design sources
Challenges & Actions | Record design/project challenges and corrective action | Problem, effect, action, owner, target date and status
Phase Summary | Summarise what was achieved and what remains | Phase status, completed work, gaps and next priorities
Group Reflection | One shared group reflection for Phase 2 | Participation, collaboration, challenges, learning and improvements
Important
Do not create a separate tracker for each activity. This Phase 2 workbook is updated as the group progresses. Evidence may include GitHub commits, screenshots, document sections, editable design links/files and other appropriate project evidence. Do not include passwords, API keys or confidential stakeholder information.

## Project Overview
Phase 2 Project Overview
Group | Tech Elite (Group L) | Phase 2 Progress Summary
Project Title | Commercial Livestock Trading Platform | Total tracked items | 12
Stakeholder / Organisation | Kgomotso Ranchu | Completed | 11
Group Leader | Boitumelo Masimong | In Progress | 0
Number of Group Members | 8 | Blocked | 0
GitHub Repository Link | Git Hub | Average completion | 91.67%
Reporting Period | 16th September 2026 -12th October 2026
Overall Phase Status | Completed | Phase 2 Reminder
Phase 2 focuses on system architecture and design. Track the design artefacts, the editable source links/files, individual contributions, challenges, Microsoft Project updates and GitHub evidence. No separate stakeholder-evidence section is required in this tracker.

## Design Progress
Phase 2 Design Progress
Task ID | Design / Project Item | Description / Expected Output | Responsible Student(s) | Planned Date | Actual Completion Date | Status | % Complete | Evidence / Link | Notes / Action Required
P2-01 | System Architecture | Overall architecture showing Flutter, ASP.NET and shared Supabase backend | Lucky Kali, Mampuku Taeli | 2021-09-26 | 08/10/2026 | Completed | 100% | https://tinyurl.com/systemArch
P2-02 | Use Case Diagram | Actors, use cases, system boundary and appropriate UML relationships | Omolemo Mangoejane | 2021-09-26 | 07/10/2026 | Completed | 100% | https://lucid.app/lucidspark/useCaseDiagram
P2-03 | Sequence Diagram 1 (Buyer) | Important Flutter process | Talente Mokgwati | 2021-09-26 | 09/10/2026 | Completed | 100% | https://www.figma.com/board/CustomerSequence
P2-04 | Sequence Diagram 2( Seller) | Important ASP.NET process | Talente Mokgwati | 2021-09-26 | 12/10/2026 | Completed | 100% | https://www.figma.com/SellerSequencce
P2-05 | ERD | Entities, attributes, PKs, FKs, relationships and cardinality | Mampuku Taeli & Lebohang Koloi | 2021-09-26 | 12/10/2026 | Completed | 100% | https://tinyurl.com/entityRelatedDiagram
P2-06 | Flutter Interface Designs | Main mobile screens and navigation | Bokang Mthembu & Rethabile Mosia | 2021-09-26 | 10/10/2026 | Completed | 100% | https://tinyurl.com/entityRelatedDiagram
P2-07 | ASP.NET Interface Designs | Main web pages and navigation | Bokang Mthembu,Rethabile Mosia,Talente Mokgwati & Lucky Kali | 2021-09-26 | 12/10/2026 | Completed | 100% | https://www.figma.com/webApp
P2-08 | Design Alignment | Requirements linked across UML, ERD and interfaces | Lebohang Koloi,Mampuku Taeli & Boitumelo Masimong | 2021-09-26 | 08/10/2026 | Completed | 100% | Already provided
P2-09 | Updated SRS | Phase 2 architecture and design section inserted in existing SRS | Omolemo Mangoejane & Lebohang Koloi | 2021-09-26 | 13/10/2026 | Completed | 100% | In the zip folder
P2-10 | Microsoft Project | Schedule updated to reflect design progress and upcoming development | Mampuku Taeli | 2021-09-26 | 30/09/2026 | Completed | 100% | In the zip folder
P2-11 | GitHub | Current design documentation and repository organisation | All Members | 2021-09-26 | 13/10/2026 | Completed | 100% | https://github.com/happinessmasimo-afk/Tech_Elites
P2-12 | Phase 2 Presentation | Presentation and defence preparation | All Members | 2021-09-26 | 15/09/2026 | Not Started | 0% | N/A

## Individual Contributions
Phase 2 Individual Contributions
Student Name | Student Number | Activity / Artefact | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Quality / Review Notes | Contribution Status
Boitumelo Masimong | 224091294 | Project management:GitHub and Progress Tracker and Microsoft Project Plan | Update the Progress Tracker as each member completes the tasks. Collaborate with team members and update the Microsoft Project Plan | Member monitered all progress and updated the progress tracker.Ensured that every member collaborated on GitHub | 12/10/2026 | 96 hours | Both documents are in the zip folder GitHub Link https://github.com/happinessmasimo-afk/Tech_Elites | Yes | 12/10/2026 | All hours were taken from the Microsoft Project Plan | Completed
Mampuku Taeli | 222082043 | Microsoft Project Plan , ERD and System Design Architecture | Update the Microsoft Project Plan and assist with refining the ERD. Member will assist with system design Architecture | Updated the Microsoft Project Schedule, all activities of the project were included and the Entity Relationship Diagram was refined. The design of the system was also completed. | 30/09/2026 | 384 hours | Link for ERD https://tinyurl.com/entityRelatedDiagram | Yes | 12/10/2026 | All hours were taken from the Microsoft Project Plan | Completed
Lebohang Koloi | 224132354 | ERD and refining documentation | Review and refine Entity Relationship Diagram. Take all diagram screenshots and update SRS | The ERD was reviewed and refined. The SRS was updated by aligning all diagrams and information with required system requirements. | 12/10/2026 | 384 hours | Updated SRS is in the zip folder | Yes | 12/10/2026 | All hours were taken from the Microsoft Project Plan | Completed
Lucky Kali | 221045002 | System Architecture Design and Interface Design | Identify all components and interactions that the system will have. Develop the interface design functionality and confirm the user requirements | Completed the system architecture by finalising the layout of the interface and make sure that the interface design is aligned with all the requirements of our stakeholder | 08/10/2026 | 72 hours | Link for System Architecture https://tinyurl.com/systemArch | Yes | 12/10/2026 | All hours were taken from the Microsoft Project Plan | Completed
Omolemo Mangoejane | 224036084 | Use Case and refining documentation | Refine Use Case diagram and assist with updating the SRS | Completed Use Case diagram by showcasing the relationship between actors, the functions of the system and all interactions between user and system | 07/10/2026 | 312 hours | Link for Use Case https://lucid.app/lucidspark/useCaseDiagram | Yes | 12/10/2026 | All hours were taken from the Microsoft Project Plan | Completed
Talente Mokgwati | 223022927 | Sequence diagram and Figma Prototype | Develop two sequence diagrams, one for a buyer and other for a seller. Assist with a Figma Prototype and show the functionality of the system | Created both sequence diagrams and developed a figma prototype to show system navigation | 09/10/2026 | 192 hours | Link for two sequence diagrams https://www.figma.com/board/CustomerSequence https://www.figma.com/SellerSequencce | Yes | 12/10/2026 | All hours were taken from the Microsoft Project Plan | Completed
Bokang Mthembu | 224063836 | Interface Design and Figma Prototype | Develop a prototype that shows layout, navigation and functionality | Developed a system interface and that assisted with a Figma Prototype that has all screens that interacts through navigation | 12/10/2026 | 432 hours | Link for Figma https://www.figma.com/design/mobileApp | Yes | 12/10/2026 | All hours were taken from the Microsoft Project Plan | Completed
Rethabile Mosia | 223013027 | Interface Design and Figma Prototype | Develop the interface and assist with Figma prototype. Ensure that all screens are consistent | Designed and refined the interface screens in Figma and ensured they are consistent | 12/10/2026 | 432 hours | Link for Figma https://www.figma.com/webApp | Yes | 12/10/2026 | All hours were taken from the Microsoft Project Plan | Completed
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started
[8 empty] | No |  |  | Not Started

## Design Source Links
Phase 2 Original Design Source Links / Files
Design Artefact | Tool Used | Editable Link / File Name | Accessible to Lecturer? | Last Updated | Responsible Student | Included in SRS? | Notes
System Architecture | Draw.IO | System Architecture | Yes | 12/10/2026 | Mampuku Taeli | Yes
Use Case Diagram | Lucid Chart | Use Case Diagram | Yes | 12/10/2026 | Omolemo Mangoejane | Yes
Sequence Diagram 1 | Figma | Sequence Diagram 1 | Yes | 12/10/2026 | Talente Mokgwati | Yes
Sequence Diagram 2 | Figma | Sequence Diagram 2 | Yes | 12/10/2026 | Talente Mokgwati | Yes
ERD | Draw.IO | Entity Relationship Diagram | Yes | 12/10/2026 | Mampuku Taeli & Lebohang Koloi | Yes
Flutter Interface Designs | Figma | Flutter Interface Design | Yes | 12/10/2026 | Rethabile Mosia , Bokang Mthembu & Talente Mokgwati | Yes
ASP.NET Interface Designs | Figma | ASP.NET Interface Design | Yes | 12/10/2026 | Rethabile Mosia , Bokang Mthembu & Talente Mokgwati | Yes
Navigation Flow | Figma | Navigation Flow | Yes | 12/10/2026 | Rethabile Mosia , Bokang Mthembu & Talente Mokgwati | Yes

## Challenges & Actions
Phase 2 Challenges and Corrective Actions
Date Identified | Challenge | Effect on Progress / Design | Corrective Action | Responsible Student | Target Date | Status | Resolved Date | Notes
23/09/2026 | Choosing the right relationship type. It was sometimes hard to decide whether two use cases should be connected with «include», «extend», or generalization, since they all look similar but mean different things. | Being uncertain about Use Case delayed other members from workinng as this UML is the foundation of Phase 2 | Reviewing examples on Ethuto , consulting with mentor and correcting the diagram | Omolemo Mangoejane | 03/10/2026 | Completed | 23/09/2026
23/09/2026 | Understanding the requirements document .The SRS was typed, so I had to figure out how to turn each requirement into the correct use case diagram symbol. | This slowed down the rate of diagram development | Review SRS, identify actors and system functionality and update diagram | Omolemo Mangoejane | 03/10/2026 | Completed | 30/09/2026
23/09/2026 | Keeping the diagram neat and easy to read . As more use cases were added, it became harder to arrange everything without the lines crossing over each other or the diagram looking cluttered. | The lines that were everywhere made it difficult to read and understand diagram | Minimise the lines that cross each other to ensure that the diagram is readable | Omolemo Mangoejane | 03/10/2026 | Completed | 26/09/2026
05/10/2026 | Member was struggling to select the most important process for a sequence diagram | This delayed the progress and made it difficult to determine interactions of the system | Review Use Case and select important processes. | Talente Mokgwati | 03/10/2026 | Completed | 05/10/2026
07/10/2026 | Poor group communication, lack of commitment, and differences in goals among group members | Poor communication delayed progress and placed all members under pressure | Ensure that all goals , deadlines , individual assignments are communicately clearly | Lebohang Koloi | 03/10/2026 | Completed | 11/10/2026
12/10/2026 | Having to wait for every member to complete their tasks , before completing the progress tracker. | Delayed progress on each task delayed members from achieving the group goal. | Reminding members to submit their progress and as they send the progress tracker is updated | Boitumelo Masimong | 03/10/2026 | Completed | 13/10/2026
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started
Not Started

## Phase Summary
Phase 2 Progress Summary
Reporting Period | 16th September 2026 -12th October 2026 | Phase 2 Completion Checklist | Complete?
Overall Phase Status | Completed | Architecture complete | Yes
What was completed during Phase 2? | All members were given tasks to do and as a result we all collaborated as this project is a team effort. The following was completed in Phase 2 : System Architecture, Use Case diagram, Two Sequence diagrams, ERD,Flutter interfaces,ASP.NET interfaces,SRS,Microsoft Project,GitHub, Links for all diagrams were included and the Progress Tracker was updated | Use Case Diagram complete | Yes
What remains incomplete? | Supabase is still incomplete | Two Sequence Diagrams complete | Yes
Why is it incomplete? | Still to be completed in Phase 3 | ERD complete | Yes
Which contributions were particularly important? | The Use Case was very important because it is the foundation of Phase 2 , without it we are unable to continue and complete the phase. All digarams were linked to each other and every contribution was important. | Flutter interfaces complete | Yes
Were there participation concerns? | Yes, as a team we had our own due date to ensure that we meet all our goals. Some members failed to submit on that day and that delayed the progress of the team. Overall eveything was sent at a later stage , but we only had less time to review eveything before submission. | ASP.NET interfaces complete | Yes
What will the group improve in Phase 3? | We will improve on communication and time management. We will work on professionalism by arriving on time and communicating consistently. We will also work on submiting on time to meet our goals as a team | Editable source links/files recorded | Yes
Main priority for Phase 3 | We will communicate with the stakeholder and show him the planned architecture of the app. The figma prototype will also be presented to him to get approval on the functionality, navigation and consistency of mobile screens. As a team we will ensure that our Phase 2 is able to assist us in Phase 3 with development, integration, testing and demonstration | SRS updated | Yes
|  | Microsoft Project updated | Yes
|  | GitHub current | Yes
|  | Individual contributions recorded | Yes
|  | Challenges/actions updated | Yes
|  | Group reflection completed | Yes

## Group Reflection
Phase 2 Group Reflection
1. What did the group complete successfully during Phase 2?
The following documents were completed successfully: System Architecture, Use Case diagram, Two Sequence diagrams, ERD,Flutter interfaces,ASP.NET interfaces,SRS,Microsoft Project,GitHub, Links for all diagrams were included and the Progress Tracker was updated
2. Which architecture or design activities were the most challenging?
Designing the figma prototype was the most challenging as it required proper planning and critical thinking. So members struggled to create interaction between screens due to the amount of screens the prototype had.
3. How did the group ensure that Flutter, ASP.NET and Supabase were designed as one integrated system?
We developed a sequence diagram that shows the relationship between Flutter, ASP.NET and Supabase as one integrated system.
4. How was work divided among group members, and was participation balanced?
Every member had someone or people to work with. Some worked in groups of two and some in groups of three. The members were paired in this order : Use Case ( Omolemo Mangoejane), ERD( Mampuku Taeli & Lebohang Koloi), Sequence Diagram ( Talente Mokgwati),System Architecture (Lucky Kali, Mampuku Taeli), Flutter Interface Designs +Navigation Flow( Bokang Mthembu, Rethabile Mosia & Talente Mokgwati),GitHub Commits(All members),Progress Tracker (Boitumelo Masimong), Microsoft Project Plan( Mampuku Taeli)
5. What did the group learn from developing the UML, ERD and interface designs?
As group we learnt that all diagrams are linked and share many components in common. UML forms the foundation of the functionality that the system will have. We learnt that the UML shows how external users and actors interact with the system. From an ERD we learnt that all objects that we have and tables should connect to tables inside the database. Interface designs help with having a visual representation of how the system will be. A prototype is a planning of how the system will be , it is not final as it can change through time.
6. What will the group do differently during development in Phase 3?
Work on our time management by submitting within the date we set for our self. Ensure that we meet more to ensure that we are all on the right track. We will also consult more to get clarity on what is required from us.