## Instructions
ITC327W Project Progress and Contribution Workbook
Use this workbook throughout the semester. Update it after each project phase and submit the same workbook again so that progress can be tracked over time.
Sheet | Purpose | Evidence and Accountability Rules
Project Overview | Enter the group and project details. The dashboard summarises task progress automatically. | 1 | Every student must be assigned meaningful work in Microsoft Project.
Task Progress | Record planned and completed tasks, responsible students, dates, status, percentage completed and evidence. | 2 | Completed work must be supported by evidence such as GitHub activity, meeting records, document sections, screenshots or stakeholder communication.
Individual Contributions | Record the work personally completed by each student. Every entry must have evidence. | 3 | GitHub commits are not the only evidence. Planning, interviewing, documentation, coordination and quality review also count.
Stakeholder Engagement | Record meetings, calls and emails with the stakeholder and the main outcomes. | 4 | Do not record work as completed by a student when it was completed by someone else.
Challenges & Actions | Record project challenges, their effect and the corrective action taken. | 5 | Do not place passwords, API keys, identity numbers, private contact details or confidential records in this workbook or on GitHub.
Phase Summary | Provide a short summary of the phase, including achievements, outstanding work and participation concerns. | 6 | The confidential individual peer evaluation must be completed separately on Blackboard.
Group Reflection | Complete one shared reflection after each phase. Be honest and specific.
Recommended Update Points
|  | Unit 1 / Phase 1 | Planning, stakeholder engagement, requirements and initial SRS
|  | Phase 2 | Architecture, UML, ERD and interface design
|  | Phase 3 | Development, integration, testing and demonstration
|  | Final | Overall project summary and final reflection

## Project Overview
Project Overview and Progress Dashboard
Project Information | Group Response | Task Status | Count
Group name or number | Tech Elite (Group L) | Completed | 19
Project title | Commercial Livestock Trading Platform | In Progress | 0
Stakeholder or organisation | Kgomotso Ranchu | Not Started | 0
Group mentor | Mr Grobbelaar | Delayed | 0
Reporting phase | Phase 2 | Blocked | 0
Reporting period | 21 September 2026 - 12 October 2026 | Overdue | 0
Overall status | Completed
Overall % complete | 95% | Contribution Summary | Count
Main achievement | The goal of Phase 2 was to take all requirements gathered in Phase 1 and create a system design that is detailed. All members of the team collaborated to make the following : System Architecture design, Use Case, Sequence Diagram, ERD, Database design, interface design(Flutter and ASP.NET) , documentation with source links, Microsoft Project, GitHub and progress Tracker. | Contribution entries | 11
Main challenge | 1.Ensuring that every diagram is consistent and represents the same idea 2. Difficulty leading the team as some members would not be present during meeting. | Verified entries | 11
Next planned activity | 1. Review all documentation to check, consistency, grammar and mistakes. 2. Update progress tracker and Microsoft plan. 3. Prepare for the presentation and submit before the 12th of October 2026. | Unverified entries | 0
|  | Stakeholder engagements | 0

## Task Progress
Task Progress Tracker
Task ID | Reporting Phase | Activity | Task Description | Assigned Student(s) | Start Date | Due Date | Status | % Complete | Evidence / Link | Verified by Group | Lecturer Comment | Progress Flag
U1-01 | Unit 1 / Phase 1 | Activity 1.1 | Identify and confirm the external stakeholder | Kali L | 20/08/26 | 31/08/26 | Completed | 100 | Stated in the Stakeholder Engagement and Evidence document | Yes |  | Completed
U1-02 | Unit 1 / Phase 1 | Activity 1.1 | Document the current process and problem | Koloi L | 20/08/26 | 31/08/26 | Completed | 100 | Stakeholder and Problem Analysis document | Yes |  | Completed
U1-03 | Unit 1 / Phase 1 | Activity 1.1 | Define the project aim, objectives and scope | Mthembu BKD | 20/08/26 | 31/08/26 | Completed | 100 | Project Scope and Integrated Solution document | Yes |  | Completed
U1-04 | Unit 1 / Phase 1 | Activity 1.2 | Prepare stakeholder interview questions | Koloi L | 20/08/26 | 31/08/26 | Completed | 100 | Stakeholder and Problem Analysis document | Yes |  | Completed
U1-05 | Unit 1 / Phase 1 | Activity 1.2 | Conduct and document the stakeholder interview | Kali L | 20/08/26 | 31/08/26 | Completed | 100 | Stakeholder Engagement and Evidence document | Yes |  | Completed
U1-06 | Unit 1 / Phase 1 | Activity 1.3 | Compile the initial SRS | Mangoejane O | 20/08/26 | 31/08/26 | Completed | 100 | Requirements Analysis and SRS document | Yes |  | Completed
U1-07 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Microsoft Project schedule | Taeli MW | 20/08/26 | 31/08/26 | Completed | 100 | Microsoft Project plan | Yes |  | Completed
U1-08 | Unit 1 / Phase 1 | Activity 1.3 | Create and configure the GitHub repository | Masimong B | 27/08/26 | 31/08/26 | Completed | 100 | GitHub | Yes |  | Completed
U1-09 | Unit 1 / Phase 1 | Activity 1.3 | Create the initial Supabase project | Kali L | 27/08/26 | 31/08/26 | Completed | 100 | Supabase | Yes |  | Completed
U1-10 | Unit 1 / Phase 1 | Activity 1.3 | Complete the progress report and contribution record | Masimong B | 28/08/26 | 31/08/26 | Completed | 100 | Progress report Excel sheet | Yes |  | Completed
U1-11 | Unit 1 / Phase 1 | Activity 1.3 | Complete the Unit 1 group reflection | All members | 28/08/26 | 31/08/26 | Completed | 100 | Documents in the zip folder | Yes |  | Completed
U2-01 | Phase 2 | Activity 3.1 | Design the System Architecture | Kali L | 21/09/26 |  | Completed | 100 |  | Yes |  | Completed
U2-02 | Phase 2 | Activity 3.2 | Develop the UML and Database Design | Koloi L,Mthembu BKD,Mangoejane O,Taeli MW, Mokgwati T | 21/09/26 |  | Completed | 100 |  | Yes |  | Completed
U2-03 | Phase 2 | Activity 3.3 | Design the User Interfaces and Finalise the System Design | All members | 21/09/26 |  | Completed | 100 |  | Yes |  | Completed
U2-04 | Phase 2 | Activity 4.1 | Set Up and Implement the Shared Supabase Backend | Kali L, Masimong B | 21/09/26 |  | Completed | 100 |  | Yes |  | Completed
U2-05 | Phase 2 | Activity 4.2 | Develop the Flutter Mobile Application | Mthembu BKD, Mokgwati T | 21/09/26 |  | Completed | 100 |  | Yes |  | Completed
U2-06 | Phase 2 | Activity 4.3 | Develop the ASP.NET Web Application | All members | 21/09/26 |  | Completed | 100 |  | Yes |  | Completed
U2-07 | Phase 2 | Activity 4.4 | Integrate the Mobile and Web Applications | All members | 21/09/26 |  | Completed | 100 |  | Yes |  | Completed
U2-08 | Phase 2 | Activity 4.4 | Updated GitHub link | All members | 21/09/26 |  | Completed | 100 |  |  |  | Completed
Formulas:
Progress Flag = IF([Task Description]="","",IF([Status]="Completed","Completed",IF([Status]="Blocked","Blocked",IF([Status]="Delayed","Delayed",IF(AND([Due Date]<>"",[Due Date]<TODAY(),[Status]<>"Completed"),"Overdue","On Track")))))

## Individual Contributions
Individual Contribution Record
Student Name | Student Number | Reporting Phase | Activity | Assigned Responsibility | Work Personally Completed | Date Completed | Hours Spent | Evidence / Link | Verified by Group | Verification Date | Notes
Boitumelo Masimong | 224091294 | Unit 1 / Phase 1 | Project management:Github and Progress Tracker | Create a GitHub repository for the project , ensure all members accept the invitation and become collaborators of the project.Allocate tasks to every member and monitor the progress. Ensure that the work of the team is recorded throughout the phase. | Completed Project Progress tracker and created a GitHub repository. | 28/08/26 | 56h | Progress tracker document | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Mampuku Taeli | 222082043 | Unit 1 / Phase 1 | Microsoft Project Plan | Create a project schedule in Microsoft Project to track activity progress, start time, end time, deadlines, milestones and get the overall project timeline. | Completed the plan on Microsoft Project and provided a timeline. | 28/08/26 | 56h | Microsoft Project Plan | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Lebohang Koloi | 224132354 | Unit 1 / Phase 1 | Stakeholder and Problem Analysis | Create a document that outlines all the problems of our Stakeholder (Kgomotso Rachu). Needs , problems and expectations are clearly defined. | Completed Stakeholder and Problem Analysis document by providing the main problems that must be solved by the team. | 28/08/26 | 48h | Stakeholder and Problem Analysis document | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Lucky Kali | 221045002 | Unit 1 / Phase 1 | Stakeholder Engagement and Evidence | Communicates directly with stakeholder,schedule a meeting and document the team's engagement with the stakeholder. Screenshot calls, texts and meeting minutes with the stakeholder. | Completed Stakeholder Engagement and Evidence document by giving meetings and communication evidence. | 28/08/26 | 48h | Stakeholder Engagement and Evidence document | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Omolemo Mangoejane | 224036084 | Unit 1 / Phase 1 | Requirements Analysis and SRS | Gather all requirements that the stakeholder expects on the app/system. Document functional, non-functional requirements and provide a requirement analysis. | Completed Requirements Analysis and SRS by providing a document that lists all requirements. The document helped to identify the main requirements , problems, users and functions of the livestock application. | 28/08/26 | 48h | Requirements Analysis and SRS document | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Talente Mokgwati | 223022927 | Unit 1 / Phase 1 | Project Risk Analysis | Identifies risks, the impact that each risk will have and mitigation plans. A risk register must be developed to assist with the risk evaluation. Member will manage risks that could affect the project. | Completed Project Risk Analysis document by providing a document that lists all risks and strategies to reduce the risks. | 28/08/26 | 48h | Project Risk Analysis document | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Bokang Mthembu | 224063836 | Unit 1 / Phase 1 | Project Scope and Integrated Solution | Defines the objectives, deliverables and elaborate on how the solution integrates with the project requirement | Completed Project Scope and Integrated Solution document by defining scope, deliverables and the project's integration solution. | 28/08/26 | 48h | Project Scope and Integrated Solution document | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Rethabile Mosia | 223013027 | Unit 1 / Phase 1 | Feasibility Analysis | Provide an analysis on technical, economic/financial, operational,schedule and organisational feasibility. This analysis will state whether the project should continue or not | Completed Feasibility Analysis document by providing technical,economic,operational and schedule and organisational feasibility of the project. | 28/08/26 | 48h | Feasibility Analysis document | Yes | 27/08/2026 | Hours spent are taken from Microsoft project plan
Boitumelo Masimong | 224091294 | Phase 2 | Project management:GitHub and Progress Tracker and Microsoft Project Plan | Update the Progress Tracker as each member completes the tasks. Collaborate with team members and update the Microsoft Project Plan | Updated both the GitHub and Progress Tracker. The progress of all group members was monitored and recorded. The Microsoft Project Plan was updated |  |  |  | Yes |  | Hours spent are taken from Microsoft project plan
Mampuku Taeli | 222082043 | Phase 2 | Microsoft Project Plan and ERD | Update the Microsoft Project Plan and assist with refining the ERD | Updated the Microsoft Project Schedule, all activities of the project were included and the Entity Relationship Diagram was refined |  |  |  | Yes |  | Hours spent are taken from Microsoft project plan
Lebohang Koloi | 224132354 | Phase 2 | ERD and refining documentation | Update the documentation that was composed in Phase 1 and assist to develop the ERD | Contributed |  |  |  | Yes |  | Hours spent are taken from Microsoft project plan
Lucky Kali | 221045002 | Phase 2 | System Design and Interface Design | [5 empty] | Yes |  | Hours spent are taken from Microsoft project plan
Omolemo Mangoejane | 224036084 | Phase 2 | Use Case and refining documentation | [5 empty] | Yes |  | Hours spent are taken from Microsoft project plan
Talente Mokgwati | 223022927 | Phase 2 | Sequence diagram and Figma Prototype | [5 empty] | Yes |  | Hours spent are taken from Microsoft project plan
Bokang Mthembu | 224063836 | Phase 2 | Interface Design and Figma Prototype | [5 empty] | Yes |  | Hours spent are taken from Microsoft project plan
Rethabile Mosia | 223013027 | Phase 2 | ERD and Figma Prototype | [5 empty] | Yes |  | Hours spent are taken from Microsoft project plan

## Stakeholder Engagement
Stakeholder Engagement Record
Date | Reporting Phase | Type of Engagement | Purpose | Students Present | Stakeholder Present / Role | Main Findings | Action Required | Evidence / Link
20/08/26 | Unit 1 / Phase 1 | Telephone Call | The meeting was held to get approval from the stakeholder. | Lucky Kali | Mr Kgomotso Rachu(Business Representative) | Lucky spoke about the stakeholder letter to get permission from the stakeholder. The stakeholder confirmed his availability. | Tech Elite requested a meeting with the stakeholder and Lucky assisted with making meeting arrangements | Stakeholder Engagement and evidence
20/08/26 | Unit 1 / Phase 1 | Meeting | The meeting was held to introduce Tech Elite (Group members) to Kgomotso Ranchu (Stakeholder). | All members(Omolemo Mangoejane, Mampuku Taeli, Lebohang Koloi,Bokang Mthembu,Rethabile Mosia, Lucky Kali,Talente Mokgwati, Boitumelo Masimong) | Mr Kgomotso Rachu(Business Representative) | The team got to understand the problem of the stakeholder, his requirements and everything was based on the needs of the business rather than our own assumptions. | The team took note of all points discussed and used them to do the documentation. The problem and requirements were analysed.The information gathered will be used to address business needs. | Stakeholder Engagement and evidence

## Challenges & Actions
Challenges and Corrective Actions
Date Identified | Reporting Phase | Challenge | Effect on Progress | Corrective Action | Responsible Student | Target Date | Status
21/08/2026 | Unit 1 / Phase 1 | Challenge faced was that the initial scope conducted by the team member was too short and not well detailed that they had to refer back to the minutes we took during our meeting with the stakeholder in order to fulfill all requirements | The member did not thoroughly go through the requirements of the stakeholder. As a result this delayed the progress of the project. | Referred to Unit 1 and Unit 2 and followed the format required. | Bokang Mthembu | 31/08/2026 | Resolved
27/08/2026 | Unit 1 / Phase 1 | Challenge faced was that the feasibility analysis provided by the member was missing the most important tasks of the project required by the stakeholder. | The feasibility analysis had to be checked and ensure that all tasks are included. As a result more time has to be allocated and this delayed feasibility analysis from being completed. | Guidance from the assesment requirements and ensure all areas were covered properly. | Rethabile Mosia | 31/08/2026 | Resolved
27/08/2026 | Unit 1 / Phase 1 | Challenges faced was not understanding how to translate information obtained from the stakeholder into a clear and well defined problem statement. | Certain aspects of the project had to be discussed again to ensure that there is clarity and this delayed the project statemrnt from being completed | Addressed this by focusing on the main issue identified during the engagement and ensuring that problem analysis reflected the stakeholder's needs rather than assumptions. | Lebohang Koloi | 31/08/2026 | Resolved
27/08/2026 | Unit 1 / Phase 1 | Challenges faced by the Microsoft Project Planner was developing a realistic and well structured project schedule. | Team member had to set more time aside to ensure that activities,responsibilities, durations and dependencies are well organised.This delayed completion of a well structured Microsoft Project Plan. | Reviewed the project requirements and regularly communicated with the group members to confirm task responsibilities, progress and expected completion dates. | Mampuku Taeli | 31/08/2026 | Resolved
20/08/2026 | Unit 1 / Phase 1 | Challenge faced was that the team member struggled to assign members to do specific tasks according to their strengths. | Certain responsibilties did not match certain member's skills, this delayed team allocations. | Communicated with the group members to understand their areas of interest and capabilities. | Boitumelo Masimong | 31/08/2026 | Resolved
27/08/2026 | Unit 1 / Phase 1 | Difficulty identifying all possible project risks at the beginning. | Some risks of the project were not taken into account. As a result this delayed the risk documentation from being completed. | Consulted with group members to identify potential risks based on their tasks and responsibilities. | Talent Mokgwati | 31/08/2026 | Resolved

## Phase Summary
Phase Progress Summary
Summary Information | Group Response | Phase Completion Checklist
Reporting phase | Unit 1 / Phase 1 | Initial or updated SRS completed | Yes
Reporting period | 20 August 2026 - 04 September 2026 | Progress report updated | Yes
Overall phase status | Completed | Individual contributions recorded | Yes
What was completed during this phase? | The following was completed in this phase: 1.Stakeholder and Problem Analysis 2.Requirements Analysis and SRS 3.Project Scope and Integrated Solution 4.Feasibility Analysis 5. Project Risk Analysis 6.Microsoft Project Plan 7.Stakeholder Engagement and Evidence 8.Project Management: GitHub and Progress Tracker 9.Supabase | Stakeholder engagement recorded | Yes
What remains incomplete? | The Github repository,Supabase are incomplete | Challenges and actions updated | Yes
Why is it incomplete? | Still to be completed in the following phases. | Group reflection completed | Yes
Which contributions were particularly important? | All contributions were important as they all assisted with the foundation of the project. This helped with having direction and knowing how to go about everything. | Microsoft Project updated | Yes
Were there participation concerns? | All members had different responsibilities and all of them contributed so we did not experience participation concerns. | GitHub evidence available | Yes
What will the group improve in the next phase? | We will improve on communication and time management. We will work on professionalism by arriving on time and communicating consistently. | Confidential peer check completed | Yes
Main priority for the next phase | The main priority is to review all documentation before submitting, gather feedback from all members from Tech Elite and update parts of the project. We will also understand how application will work in terms of architecture and how different users can use the application.

## Group Reflection
Group Reflection
Reflection Information | Group Response | Reflection Guidance
Reporting phase | Unit 1 / Phase 1 | Length | Approximately 300–400 words in total.
Project title | Commercial Livestock Marketplace and Record-Keeping Application | Focus | Discuss the group’s actual experience, not the activity instructions.
Most important learning from this phase | The most important learning from phase 1 was planning properly, communicating effectively and having clear requirements before starting to build the app. The skill of time management became a lesson in this phase as we had to manage our time well to meet our goals and submit on time. The power of communication was also important as we had to share ideas, brainstorm and make decisions as a team . In every big decision taken we had to vote and majority will rule on the particular topic. For example, we had to agree on the group name (Tech Elite). We also got to learn how it's important to collaborate on the project. As each member had different responsibilities, we set time aside to let each member walk us through what they were assigned to do. | Honesty | Identifying a genuine challenge will not disadvantage the group when an improvement action is provided.
What went well and why? | What went well:We are a hardworking team and we were able to work together. In every challenge we experienced we were able to support each other and ensure that we produce quality work. As Tech Elite we were able to share ideas and solutions. As we faced challenges we tried to tackle them as a team. This worked well as it helped us to collaborate, communicate , plan and make decisions together. Every member took their skills and as we collaborated we got to see the strength of the the group. Each contribution from every member made the planning of the project successful. | Evidence | Ensure that claims about participation agree with the contribution record, Microsoft Project and GitHub.
What was difficult and why? | Each member had different skills and ideas to offer. It was difficult to assign a responsibilty to each team member. At some point we faced difficulty with communication and making sure that every member understood the project requirements. This delayed the progress of the project as some members could not complete their responsibilities. | Research use | Student work may only be used for research after the required ethical approval and consent processes.
How were tasks divided among members? | Tasks were divided evenly among members. Each member was tasked with a responsibility and each member received one topic to work on. Some tasks required more time, research and others needed less. Amount of topic was the same but effort that each member has to apply was different. Each member had their own task and had to do research on their task. We then arranged a meeting as a team where we reviewed and discussed every part of Phase 1. The meeting was used to monitor every member's task and make changes where needed.
Did all members contribute fairly? Explain. | Yes, every member made sure that they do their part , they contributed ideas and we made sure we support each other as a team.
How did the group handle disagreements or delays? | Whenever we disagreed on something we ultimately voted. If majority of the team picks something we made sure we settle on the point that is mostly voted for.
What did the group learn from the stakeholder? | We learned about how apps are important for every business especially ones that want to advance to digital platforms
Improvement action 1 for the next phase | Communicate effectively and ensure that we are all on the same page
Improvement action 2 for the next phase | Arriving on time for our meetings and submitting tasks on time
Priority for the next phase | Work on the architecture of the project